Stewardship Campaign

Schedule Overview

Here’s a quick overview of the stewardship campaign schedule, with one month each for the following program phases: planning, getting started, campaign underway, Consecration and Celebration Sundays, and follow-up. For a more detailed schedule, see “Tasks and Resources by Month and Week,” in Chapter 2: Implementation.

Using this schedule will help keep your campaign on track in the coming weeks. If you like, create your own campaign to-do list on the page following this overview.

Planning (Month ___________________________ )

- Planning and Budget Review and Approval

- Order copies of Enough program components:

- Book

- DVD

- Leader Guide

- Stewardship Program Guide with Campaign Resource Download

- Review this Stewardship Guide and decide which items may need to be designed and printed. This might include items such as commitment cards, bookmarks, giving guide, signage, and so forth. Sample copy and graphics for many of these items can be found in the Communication Resources and Art Resources folders in this download. Be sure to allocate plenty of time to receive the items before your first usage.

- Other: ____________________

Getting Started (Month ___________________________ )

Weeks 1–2: Upload introductory materials to website.

Week 3: Distribute books, DVD, and Leader Guide.

Week 4: Mailing #1 sent out.

Campaign Underway (Month ___________________________ )

Week 1: 
Upload sermon, e-mail, and bulletin article to website. Mailing #2 goes out. 
Small group study begins with Session 1.

Week 2: 
Upload sermon, e-mail, bulletin article, and bulletin inserts to website. 
Small group study continues with Session 2.

Week 3: 
Upload sermon, e-mail, and bulletin article to website. Small group study continues with Session 3.

Week 4: 
Upload sermon, e-mail, and pledging tools to website. Mailing #3 goes out. Small group study concludes with Session 4.

Consecration and Celebration Sundays (Month ___________________________ )

Week 1: 
First Consecration Sunday. Distribute additional commitment cards.
Distribute thank-you gifts.

Week 2: Second Consecration Sunday. Distribute additional commitment cards.

Week 3: Follow-up calls begin.

Week 4: Celebration Sunday. Share results of the stewardship campaign.

Follow-up (Month ___________________________ )

Week 1: Valued member survey mailed to nonresponding members.